## dataset
id | assigned_date | project_name | country | city | standard_program | status | kick_off | design_start | design_completed | delivery_start | delivery_completed | handover | design_manager | delivery_manager
P-26130 | 2021-03-18 | project - 4870 | Argentina | Buenos Aires | 120 | completed | 2021-03-21 | 2021-03-22 | 2021-04-28 | 2021-04-29 | 2021-09-02 | 2021-09-08 | Michael Brown | Emily Johnson
P-76358 | 2020-06-09 | project - 6369 | Argentina | Buenos Aires | 120 | completed | 2020-06-10 | 2020-06-11 | 2020-07-08 | 2020-07-08 | 2020-11-17 | 2020-11-23 | Jane Smith | Emily Johnson
P-80029 | 2021-11-14 | project - 8581 | Argentina | Buenos Aires | 120 | completed | 2021-11-19 | 2021-11-21 | 2021-12-23 | 2021-12-26 | 2022-05-14 | 2022-05-24 | Michael Brown | Emily Johnson
P-20236 | 2021-10-11 | project - 7150 | Australia | Sydney | 120 | completed | 2021-10-15 | 2021-10-16 | 2021-11-28 | 2021-12-01 | 2022-04-18 | 2022-04-28 | John Doe | Emily Johnson
P-24569 | 2022-02-05 | project - 8217 | Australia | Sydney | 120 | completed | 2022-02-09 | 2022-02-11 | 2022-03-19 | 2022-03-20 | 2022-07-11 | 2022-07-21 | Michael Brown | Andrew Wilson
P-27194 | 2023-07-25 | project - 2575 | Australia | Sydney | 120 | assigned | [6 empty] | Michael Brown | David Lee
P-33103 | 2020-08-01 | project - 1633 | Australia | Sydney | 120 | completed | 2020-08-02 | 2020-08-03 | 2020-09-21 | 2020-09-23 | 2020-12-29 | 2021-01-03 | Michael Brown | David Lee
P-47992 | 2022-10-09 | project - 2985 | Australia | Sydney | 120 | completed | 2022-10-11 | 2022-10-11 | 2022-11-05 | 2022-11-05 | 2023-03-07 | 2023-03-13 | John Doe | Emily Johnson
P-59727 | 2022-11-28 | project - 7665 | Australia | Sydney | 120 | completed | 2022-12-01 | 2022-12-02 | 2023-01-15 | 2023-01-15 | 2023-04-26 | 2023-05-05 | Jane Smith | David Lee
P-65143 | 2021-06-04 | project - 3514 | Australia | Sydney | 120 | completed | 2021-06-09 | 2021-06-09 | 2021-07-24 | 2021-07-26 | 2021-10-21 | 2021-10-28 | Jane Smith | David Lee
P-77175 | 2022-05-10 | project - 4099 | Australia | Sydney | 120 | completed | 2022-05-15 | 2022-05-17 | 2022-06-17 | 2022-06-17 | 2022-09-21 | 2022-09-26 | Michael Brown | Emily Johnson
P-15985 | 2020-02-13 | project - 1968 | Brazil | São Paulo | 120 | completed | 2020-02-16 | 2020-02-16 | 2020-03-15 | 2020-03-17 | 2020-07-22 | 2020-07-29 | Michael Brown | Andrew Wilson
P-32549 | 2021-02-11 | project - 2674 | Brazil | São Paulo | 120 | completed | 2021-02-14 | 2021-02-15 | 2021-03-31 | 2021-04-01 | 2021-07-27 | 2021-08-01 | John Doe | David Lee
P-40111 | 2021-03-11 | project - 3644 | Brazil | São Paulo | 120 | completed | 2021-03-16 | 2021-03-16 | 2021-04-18 | 2021-04-21 | 2021-07-25 | 2021-07-31 | John Doe | Andrew Wilson
P-67833 | 2022-05-13 | project - 2469 | Brazil | São Paulo | 120 | completed | 2022-05-15 | 2022-05-17 | 2022-07-06 | 2022-07-08 | 2022-10-21 | 2022-10-29 | Michael Brown | Emily Johnson
P-87277 | 2021-10-07 | project - 2120 | Brazil | São Paulo | 120 | completed | 2021-10-11 | 2021-10-12 | 2021-11-29 | 2021-11-30 | 2022-03-05 | 2022-03-11 | Jane Smith | Emily Johnson
P-87669 | 2020-06-21 | project - 7898 | Brazil | Salvador | 120 | completed | 2020-06-22 | 2020-06-22 | 2020-07-28 | 2020-07-28 | 2020-11-12 | 2020-11-17 | Jane Smith | David Lee
P-20453 | 2021-03-20 | project - 7035 | Canada | Toronto | 120 | completed | 2021-03-22 | 2021-03-22 | 2021-05-07 | 2021-05-08 | 2021-09-19 | 2021-09-29 | Michael Brown | Emily Johnson
P-29208 | 2020-03-03 | project - 7676 | Canada | Toronto | 120 | completed | 2020-03-07 | 2020-03-07 | 2020-04-01 | 2020-04-04 | 2020-08-21 | 2020-08-29 | Jane Smith | Emily Johnson
P-88054 | 2022-02-22 | project - 2197 | Canada | Toronto | 120 | completed | 2022-02-26 | 2022-02-28 | 2022-04-12 | 2022-04-13 | 2022-07-23 | 2022-07-30 | Jane Smith | Emily Johnson
P-15252 | 2020-01-06 | project - 4556 | China | Beijing | 120 | completed | 2020-01-09 | 2020-01-11 | 2020-02-14 | 2020-02-15 | 2020-06-28 | 2020-07-04 | John Doe | David Lee
P-16516 | 2022-03-12 | project - 1448 | China | Guangzhou | 120 | completed | 2022-03-13 | 2022-03-14 | 2022-04-28 | 2022-04-30 | 2022-09-09 | 2022-09-15 | Jane Smith | Andrew Wilson
P-17129 | 2020-04-18 | project - 8747 | China | Guangzhou | 120 | completed | 2020-04-20 | 2020-04-22 | 2020-06-09 | 2020-06-09 | 2020-09-16 | 2020-09-24 | John Doe | Emily Johnson
P-23141 | 2023-05-24 | project - 4110 | China | Guangzhou | 120 | kick off | 2023-05-25 | 2023-05-27 | 2023-06-27 | 2023-06-27 | 2023-09-25 | 2023-10-04 | Jane Smith | David Lee
P-26664 | 2022-12-13 | project - 5871 | China | Beijing | 120 | completed | 2022-12-17 | 2022-12-19 | 2023-01-28 | 2023-01-30 | 2023-05-13 | 2023-05-19 | Michael Brown | David Lee
P-58681 | 2023-07-07 | project - 3679 | China | Shenzhen | 120 | design | 2023-07-08 | [5 empty] | John Doe | David Lee
P-66878 | 2023-07-16 | project - 1844 | China | Shenzhen | 120 | delivery | 2023-07-21 | 2023-07-23 | 2023-09-05 | 2023-09-05 |  |  | John Doe | Emily Johnson
P-73364 | 2021-09-15 | project - 7714 | China | Shenzhen | 120 | completed | 2021-09-20 | 2021-09-20 | 2021-10-19 | 2021-10-22 | 2022-02-13 | 2022-02-20 | Michael Brown | Andrew Wilson
P-76462 | 2021-06-15 | project - 8132 | China | Beijing | 120 | completed | 2021-06-17 | 2021-06-18 | 2021-07-29 | 2021-07-29 | 2021-11-15 | 2021-11-22 | Michael Brown | Andrew Wilson
P-89429 | 2020-11-23 | project - 4393 | China | Guangzhou | 120 | completed | 2020-11-25 | 2020-11-27 | 2021-01-13 | 2021-01-14 | 2021-04-25 | 2021-04-30 | Michael Brown | Andrew Wilson
P-34395 | 2021-07-12 | project - 4996 | Egypt | Cairo | 120 | completed | 2021-07-15 | 2021-07-16 | 2021-08-18 | 2021-08-21 | 2021-12-03 | 2021-12-11 | Michael Brown | Andrew Wilson
P-46056 | 2022-02-23 | project - 4044 | Egypt | Cairo | 120 | completed | 2022-02-28 | 2022-03-01 | 2022-04-08 | 2022-04-08 | 2022-08-23 | 2022-09-01 | Jane Smith | Andrew Wilson
P-75876 | 2022-06-25 | project - 9197 | Egypt | Alexandria | 120 | completed | 2022-06-29 | 2022-06-29 | 2022-07-30 | 2022-07-31 | 2022-11-10 | 2022-11-20 | John Doe | David Lee
P-77692 | 2021-10-25 | project - 9322 | Egypt | Alexandria | 90 | completed | 2021-10-26 | 2021-10-26 | 2021-12-01 | 2021-12-03 | 2022-04-14 | 2022-04-22 | Michael Brown | Emily Johnson
P-92730 | 2023-04-30 | project - 3604 | Egypt | Cairo | 120 | design | 2023-05-04 | 2023-05-06 |  |  |  |  | Jane Smith | David Lee
P-14087 | 2023-04-14 | project - 7982 | France | Lyon | 120 | design | 2023-04-15 | 2023-04-15 |  |  |  |  | John Doe | David Lee
P-22554 | 2020-06-09 | project - 6459 | France | Paris | 120 | completed | 2020-06-11 | 2020-06-13 | 2020-07-21 | 2020-07-22 | 2020-10-17 | 2020-10-26 | Jane Smith | David Lee
P-23600 | 2020-05-10 | project - 5998 | France | Marseille | 120 | completed | 2020-05-12 | 2020-05-13 | 2020-06-13 | 2020-06-16 | 2020-10-04 | 2020-10-09 | John Doe | Andrew Wilson
P-38212 | 2021-12-20 | project - 9154 | France | Lyon | 120 | completed | 2021-12-22 | 2021-12-23 | 2022-02-04 | 2022-02-06 | 2022-05-07 | 2022-05-17 | John Doe | Emily Johnson
P-67662 | 2023-02-01 | project - 3594 | France | Lyon | 120 | design | 2023-02-03 | 2023-02-04 |  |  |  |  | Michael Brown | David Lee
P-69286 | 2020-05-10 | project - 2890 | France | Paris | 90 | completed | 2020-05-12 | 2020-05-13 | 2020-07-02 | 2020-07-04 | 2020-10-15 | 2020-10-24 | John Doe | Emily Johnson
P-75551 | 2021-09-12 | project - 8608 | France | Lyon | 120 | completed | 2021-09-17 | 2021-09-17 | 2021-10-24 | 2021-10-24 | 2022-02-04 | 2022-02-11 | John Doe | David Lee
P-94068 | 2020-10-13 | project - 9664 | France | Paris | 120 | completed | 2020-10-16 | 2020-10-16 | 2020-11-28 | 2020-11-29 | 2021-04-08 | 2021-04-17 | Jane Smith | Andrew Wilson
P-95034 | 2021-10-05 | project - 2978 | France | Paris | 90 | completed | 2021-10-08 | 2021-10-09 | 2021-11-07 | 2021-11-10 | 2022-03-27 | 2022-04-04 | Jane Smith | Andrew Wilson
P-25490 | 2020-04-09 | project - 5778 | Germany | Berlin | 90 | completed | 2020-04-12 | 2020-04-12 | 2020-05-20 | 2020-05-22 | 2020-09-14 | 2020-09-19 | Jane Smith | David Lee
P-38613 | 2022-05-18 | project - 9959 | Germany | Munich | 120 | completed | 2022-05-21 | 2022-05-23 | 2022-07-05 | 2022-07-07 | 2022-10-27 | 2022-11-01 | John Doe | Andrew Wilson
P-38995 | 2022-03-09 | project - 4818 | Germany | Hamburg | 120 | completed | 2022-03-13 | 2022-03-13 | 2022-04-07 | 2022-04-09 | 2022-08-02 | 2022-08-11 | John Doe | Andrew Wilson
P-72132 | 2022-09-04 | project - 9719 | Germany | Munich | 120 | completed | 2022-09-08 | 2022-09-09 | 2022-10-26 | 2022-10-29 | 2023-02-12 | 2023-02-21 | Jane Smith | Emily Johnson
P-97223 | 2020-09-06 | project - 8827 | Germany | Munich | 120 | completed | 2020-09-10 | 2020-09-10 | 2020-10-21 | 2020-10-23 | 2021-03-11 | 2021-03-20 | Michael Brown | David Lee
P-14796 | 2020-07-19 | project - 6467 | India | Mumbai | 120 | completed | 2020-07-22 | 2020-07-24 | 2020-08-27 | 2020-08-28 | 2021-01-05 | 2021-01-11 | Jane Smith | David Lee
P-16412 | 2023-01-27 | project - 8793 | India | Agra | 120 | delivery | 2023-01-30 | 2023-01-31 | 2023-03-07 | 2023-03-09 |  |  | Michael Brown | Andrew Wilson
P-37440 | 2023-01-22 | project - 6238 | India | Delhi | 120 | delivery | 2023-01-27 | 2023-01-27 | 2023-03-16 | 2023-03-17 |  |  | Jane Smith | Emily Johnson
P-39707 | 2021-10-20 | project - 4361 | India | Mumbai | 120 | completed | 2021-10-21 | 2021-10-21 | 2021-11-18 | 2021-11-19 | 2022-03-12 | 2022-03-22 | John Doe | Emily Johnson
P-40964 | 2021-03-22 | project - 5388 | India | Agra | 120 | completed | 2021-03-24 | 2021-03-25 | 2021-04-22 | 2021-04-24 | 2021-08-12 | 2021-08-20 | Jane Smith | David Lee
P-41892 | 2022-07-28 | project - 6166 | India | Kolkata | 120 | completed | 2022-07-31 | 2022-07-31 | 2022-09-19 | 2022-09-19 | 2023-01-18 | 2023-01-23 | John Doe | Emily Johnson
P-42363 | 2022-07-28 | project - 4120 | India | Agra | 120 | completed | 2022-07-31 | 2022-08-01 | 2022-09-13 | 2022-09-13 | 2022-12-15 | 2022-12-24 | Jane Smith | Andrew Wilson
P-84490 | 2022-09-15 | project - 6394 | India | Delhi | 120 | completed | 2022-09-19 | 2022-09-20 | 2022-11-06 | 2022-11-09 | 2023-03-24 | 2023-04-03 | Michael Brown | David Lee
P-96095 | 2020-10-03 | project - 1371 | India | Mumbai | 120 | completed | 2020-10-06 | 2020-10-08 | 2020-11-02 | 2020-11-03 | 2021-02-02 | 2021-02-12 | Jane Smith | Andrew Wilson
P-13743 | 2022-12-07 | project - 3395 | Italy | Florence | 120 | completed | 2022-12-11 | 2022-12-11 | 2023-01-24 | 2023-01-25 | 2023-05-24 | 2023-06-03 | Michael Brown | Andrew Wilson
P-27852 | 2020-01-15 | project - 8146 | Italy | Naples | 120 | completed | 2020-01-18 | 2020-01-18 | 2020-03-06 | 2020-03-09 | 2020-07-25 | 2020-08-02 | Jane Smith | Emily Johnson
P-57944 | 2022-07-19 | project - 1419 | Italy | Naples | 120 | completed | 2022-07-20 | 2022-07-22 | 2022-09-08 | 2022-09-11 | 2022-12-05 | 2022-12-14 | Jane Smith | Andrew Wilson
P-59453 | 2021-07-02 | project - 2389 | Italy | Florence | 120 | completed | 2021-07-04 | 2021-07-05 | 2021-08-01 | 2021-08-02 | 2021-12-11 | 2021-12-16 | John Doe | Emily Johnson
P-91544 | 2021-08-12 | project - 2624 | Italy | Rome | 120 | completed | 2021-08-13 | 2021-08-13 | 2021-09-29 | 2021-10-01 | 2022-02-07 | 2022-02-14 | Michael Brown | Andrew Wilson
P-92802 | 2020-12-04 | project - 4607 | Italy | Rome | 120 | completed | 2020-12-07 | 2020-12-09 | 2021-01-23 | 2021-01-25 | 2021-05-31 | 2021-06-05 | John Doe | Emily Johnson
P-39328 | 2021-01-11 | project - 3097 | Japan | Kyoto | 120 | completed | 2021-01-12 | 2021-01-12 | 2021-02-28 | 2021-03-02 | 2021-06-03 | 2021-06-11 | Michael Brown | Andrew Wilson
P-79565 | 2020-07-19 | project - 9822 | Japan | Kyoto | 120 | completed | 2020-07-21 | 2020-07-21 | 2020-08-24 | 2020-08-27 | 2020-12-12 | 2020-12-17 | Jane Smith | Andrew Wilson
P-46540 | 2022-12-20 | project - 1771 | Malaysia | Penang | 120 | completed | 2022-12-21 | 2022-12-21 | 2023-01-24 | 2023-01-26 | 2023-05-12 | 2023-05-22 | John Doe | Emily Johnson
P-74640 | 2020-08-09 | project - 6802 | Malaysia | Penang | 120 | completed | 2020-08-11 | 2020-08-13 | 2020-10-01 | 2020-10-04 | 2021-01-16 | 2021-01-26 | Jane Smith | Andrew Wilson
P-96374 | 2021-04-19 | project - 1583 | Malaysia | Kuala Lumpur | 120 | completed | 2021-04-22 | 2021-04-22 | 2021-05-26 | 2021-05-28 | 2021-09-19 | 2021-09-27 | Michael Brown | Emily Johnson
P-96997 | 2021-02-09 | project - 3481 | Malaysia | Penang | 90 | completed | 2021-02-13 | 2021-02-13 | 2021-03-13 | 2021-03-13 | 2021-07-23 | 2021-07-30 | Michael Brown | David Lee
P-18665 | 2020-06-01 | project - 1326 | Mexico | Guadalajara | 120 | completed | 2020-06-03 | 2020-06-04 | 2020-07-05 | 2020-07-08 | 2020-11-11 | 2020-11-20 | Jane Smith | Andrew Wilson
P-29111 | 2020-02-12 | project - 7329 | Mexico | Monterrey | 90 | completed | 2020-02-14 | 2020-02-14 | 2020-03-27 | 2020-03-29 | 2020-07-07 | 2020-07-13 | Michael Brown | Andrew Wilson
P-52711 | 2022-06-26 | project - 3525 | Mexico | Mexico City | 120 | completed | 2022-06-29 | 2022-06-29 | 2022-08-02 | 2022-08-04 | 2022-11-01 | 2022-11-09 | John Doe | David Lee
P-54569 | 2021-10-09 | project - 2399 | Mexico | Monterrey | 120 | completed | 2021-10-14 | 2021-10-16 | 2021-12-04 | 2021-12-07 | 2022-03-11 | 2022-03-16 | Jane Smith | David Lee
P-58862 | 2021-05-06 | project - 7961 | Mexico | Guadalajara | 120 | completed | 2021-05-07 | 2021-05-09 | 2021-06-08 | 2021-06-10 | 2021-10-03 | 2021-10-12 | Michael Brown | Emily Johnson
P-59521 | 2023-05-16 | project - 2378 | Mexico | Guadalajara | 120 | design | 2023-05-18 | 2023-05-18 |  |  |  |  | John Doe | Andrew Wilson
P-66962 | 2021-05-17 | project - 1683 | Mexico | Mexico City | 120 | completed | 2021-05-21 | 2021-05-21 | 2021-06-28 | 2021-06-28 | 2021-10-24 | 2021-11-01 | Michael Brown | David Lee
P-77176 | 2021-09-30 | project - 6772 | Mexico | Guadalajara | 120 | completed | 2021-10-04 | 2021-10-06 | 2021-11-25 | 2021-11-26 | 2022-04-10 | 2022-04-18 | John Doe | David Lee
P-91579 | 2022-10-19 | project - 2566 | Mexico | Monterrey | 120 | completed | 2022-10-22 | 2022-10-22 | 2022-11-28 | 2022-11-29 | 2023-04-13 | 2023-04-23 | John Doe | Emily Johnson
P-13205 | 2020-11-21 | project - 4917 | Russia | Moscow | 120 | completed | 2020-11-25 | 2020-11-26 | 2020-12-23 | 2020-12-25 | 2021-03-22 | 2021-03-28 | John Doe | David Lee
P-83001 | 2022-07-29 | project - 4927 | Russia | Moscow | 120 | completed | 2022-07-30 | 2022-07-30 | 2022-09-02 | 2022-09-02 | 2023-01-04 | 2023-01-10 | Michael Brown | David Lee
P-31425 | 2022-02-01 | project - 1458 | South Africa | Port Elizabeth | 120 | completed | 2022-02-04 | 2022-02-04 | 2022-03-07 | 2022-03-07 | 2022-06-17 | 2022-06-24 | John Doe | Emily Johnson
P-36162 | 2022-12-23 | project - 6605 | South Africa | Johannesburg | 120 | completed | 2022-12-26 | 2022-12-27 | 2023-01-23 | 2023-01-25 | 2023-06-12 | 2023-06-19 | Michael Brown | Andrew Wilson
P-53309 | 2022-06-03 | project - 5802 | South Africa | Johannesburg | 120 | completed | 2022-06-07 | 2022-06-08 | 2022-07-28 | 2022-07-30 | 2022-11-20 | 2022-11-25 | Michael Brown | David Lee
P-57332 | 2022-10-02 | project - 7637 | South Africa | Port Elizabeth | 120 | completed | 2022-10-03 | 2022-10-03 | 2022-11-16 | 2022-11-17 | 2023-02-12 | 2023-02-19 | John Doe | David Lee
P-58055 | 2021-06-02 | project - 6964 | South Africa | Cape Town | 120 | completed | 2021-06-03 | 2021-06-05 | 2021-07-09 | 2021-07-12 | 2021-11-25 | 2021-12-03 | Jane Smith | David Lee
P-75536 | 2021-08-04 | project - 9231 | South Africa | Cape Town | 120 | completed | 2021-08-06 | 2021-08-06 | 2021-09-17 | 2021-09-17 | 2022-01-06 | 2022-01-15 | John Doe | David Lee
P-91266 | 2021-01-22 | project - 7220 | South Africa | Cape Town | 120 | completed | 2021-01-27 | 2021-01-27 | 2021-03-06 | 2021-03-09 | 2021-06-09 | 2021-06-19 | John Doe | Andrew Wilson
P-92490 | 2022-01-02 | project - 6190 | South Africa | Port Elizabeth | 120 | completed | 2022-01-04 | 2022-01-06 | 2022-02-17 | 2022-02-17 | 2022-07-05 | 2022-07-10 | Michael Brown | David Lee
P-89323 | 2020-10-18 | project - 2201 | South Korea | Seoul | 120 | completed | 2020-10-20 | 2020-10-22 | 2020-12-07 | 2020-12-09 | 2021-03-06 | 2021-03-11 | John Doe | Andrew Wilson
P-93259 | 2020-09-27 | project - 3487 | South Korea | Seoul | 120 | completed | 2020-09-28 | 2020-09-28 | 2020-11-17 | 2020-11-19 | 2021-03-12 | 2021-03-22 | John Doe | David Lee
P-42075 | 2020-07-29 | project - 2182 | Spain | Madrid | 120 | completed | 2020-08-03 | 2020-08-04 | 2020-08-31 | 2020-08-31 | 2021-01-17 | 2021-01-26 | Jane Smith | Andrew Wilson
P-44972 | 2020-08-06 | project - 8469 | Spain | Madrid | 90 | completed | 2020-08-07 | 2020-08-08 | 2020-09-16 | 2020-09-19 | 2020-12-24 | 2021-01-03 | John Doe | Andrew Wilson
P-76526 | 2023-07-06 | project - 3643 | Spain | Madrid | 120 | design | 2023-07-10 | 2023-07-10 |  |  |  |  | John Doe | David Lee
P-81867 | 2021-01-11 | project - 4472 | Spain | Barcelona | 120 | completed | 2021-01-12 | 2021-01-14 | 2021-03-03 | 2021-03-04 | 2021-07-09 | 2021-07-19 | Michael Brown | Andrew Wilson
P-98969 | 2022-01-16 | project - 4494 | Spain | Madrid | 120 | completed | 2022-01-20 | 2022-01-20 | 2022-03-06 | 2022-03-09 | 2022-06-10 | 2022-06-15 | Jane Smith | Emily Johnson
P-87234 | 2021-03-16 | project - 2188 | Spain | Madrid | 120 | completed | 2021-03-21 | 2021-03-21 | 2021-04-25 | 2021-04-28 | 2021-08-04 | 2021-08-10 | Michael Brown | Andrew Wilson
P-13378 | 2022-03-11 | project - 7635 | United Kingdom | London | 120 | completed | 2022-03-14 | 2022-03-16 | 2022-05-02 | 2022-05-04 | 2022-08-23 | 2022-08-29 | Michael Brown | David Lee
P-49931 | 2020-04-23 | project - 3787 | United Kingdom | London | 120 | completed | 2020-04-25 | 2020-04-26 | 2020-06-10 | 2020-06-11 | 2020-09-17 | 2020-09-27 | John Doe | Emily Johnson
P-79769 | 2021-05-20 | project - 7597 | United Kingdom | London | 120 | completed | 2021-05-22 | 2021-05-23 | 2021-06-22 | 2021-06-24 | 2021-10-28 | 2021-11-07 | Jane Smith | Emily Johnson